## Sheet1
Stages
Staff | Kickoff | Design Phase | Build Phase | Training Phase |  | Implementation Phase
Project Analysis | 6 Days / 8hours
Requirement Gathering | 6 Days / 8hours
Client Interview | 1 Day / 2 hours
Plan Project | 6 Days / 8hours
Promote Project Plan | 6 Days / 8hours |  |  | Promote Project Plan | 7 Days / 8hours
Update Plan | 1 Day / 1 hour |  |  | Update Plan | 2 Day / 1 hour
Project Proposal/Approval | 1 Day/ 1 hour |  |  | Project Proposal/Approval | 2 Day/ 1 hour
Analyze Client System | 6 Days / 8hours |  |  | Analyze Client System | 7 Days / 8hours
Total Duration | 33 days |  |  | Total Duration | 34 days
Prepare Basic layout |  | 4 days / 8hours |  | Prepare Basic layout
Prepare Diagrams |  | 1 day / 2 hours |  | Prepare Diagrams
Develop Diagrams |  | 4 days / 8hours |  | Develop Diagrams
Prepare Precise Layout |  | 1 day / 2hours |  | Prepare Precise Layout
Prepare Final Diagrams |  | 4 days / 8hours |  | Prepare Final Diagrams
Total Duration |  | 14 days |  | Total Duration
Gantt Chart |  | 7 Days / 10 hours |  | Gantt Chart
Project Charter |  | 5 Days / 4 hours |  | Project Charter
Scope of work |  | 7 Days / 7 hours |  | Scope of work
Vision and scope document |  | 5 Days / 10 hours |  | Vision and scope document
Total Duration |  | 24 days |  | Total Duration
30 day / 12 hours
Software Preparation |  |  | 1 days / 1 hour | Software Preparation
Software Approval |  |  | 20days / 12 hours | Software Approval
Software Coding |  |  | 20days / 12 hours | Software Coding
Computation Algoritm |  |  | 20days / 12 hours | Computation Algoritm
Total Duration |  |  | 100 days | Total Duration
Training |  |  |  | 2 days / 12hours
Total Duration |  |  |  | 2 days
4 days / 12 hours
Testing | [6 empty] | 4 days / 12 hours
Debugging | [6 empty] | 2 days / 12 hours
Quality Assurance | [7 empty] | Overall Time: 61 days 1464 hours
Total Duration